CareTech

Project Management Documentation

Hospital Food & Maintenance Management System

| Team Leader | Hasnaa Montaser Youssef |
| --- | --- |
| Team Member | Abeer Abdelrameed |
| University | Hurghada University — Faculty of Computer Science |
| Planning Period | 5 October 2026 – 1 January 2027 |
| Submission Date | 2 January 2027 |

This document describes the project-management plan, development phases, task schedule, tools, risk controls, and expected deliverables. The plan is based on the CareTech project details and GanttProject schedule provided.

# 1. Project Overview

CareTech is the project name for the Hospital Food & Maintenance Management System. The system enables patients to request meals and report maintenance problems while authorized hospital staff manage and track these requests.

# 2. Project Management Objectives

Define the project scope, objectives, users, and requirements before implementation.

Break work into manageable tasks and schedule them in a logical order.

Estimate task start dates, end dates, and durations.

Coordinate database, frontend, backend, integration, testing, and delivery.

Monitor progress and identify delays or risks early.

# 3. Project Scope

Food Ordering: view available meals, submit food orders, and track order status.

Maintenance Management: report room or facility problems, assign requests, and track progress.

User Roles: Patient, Food Department Staff, Maintenance Staff, and Admin.

Request Tracking: statuses show the progress of food and maintenance requests.

# 4. Project Management Tools

| Purpose | Tool | Use |
| --- | --- | --- |
| Planning and task tracking | Trello | Organize tasks, documentation, and progress. |
| Scheduling | GanttProject | Create timeline, task durations, and dependencies. |
| Communication | WhatsApp | Coordinate updates and decisions. |
| Documentation | Microsoft Word / PDF | Prepare and share project documentation. |
| Version control | Git and GitHub | Store project files and maintain a shared record. |

# 5. Project Schedule

The final submission is scheduled for 2 January 2027. Therefore, all planned project work and delivery preparation must finish by 1 January 2027.

| Phase | Start Date | End Date | Duration |
| --- | --- | --- | --- |
| 1. Requirements Analysis | 05/10/2026 | 12/10/2026 | 6 days |
| 2. System Design | 13/10/2026 | 24/10/2026 | 8 days |
| 3. Database Development | 25/10/2026 | 07/11/2026 | 10 days |
| 4. Frontend Development | 08/11/2026 | 28/11/2026 | 15 days |
| 5. Backend Development | 16/11/2026 | 05/12/2026 | 14 days |
| 6. Integration & Testing | 06/12/2026 | 19/12/2026 | 10 days |
| 7. Documentation & Delivery | 20/12/2026 | 01/01/2027 | 13 days |

Scheduling note: Frontend and backend development overlap, allowing both components to progress before integration and testing.

# 6. Phase Tasks

## 1. Requirements Analysis (05/10/2026–12/10/2026)

Define project scope and objectives (05/10–06/10)

Identify users and roles (07/10–08/10)

Define functional requirements (09/10–10/10)

Define non-functional requirements (11/10–12/10)

## 2. System Design (13/10/2026–24/10/2026)

Create Use Case Diagram (13/10–15/10)

Create Activity Diagrams (16/10–18/10)

Design ERD (19/10–21/10)

Design UI wireframes (22/10–24/10)

## 3. Database Development (25/10/2026–07/11/2026)

Create database and tables (25/10–28/10)

Define keys and relationships (29/10–02/11)

Insert initial data (03/11–05/11)

Test database (06/11–07/11)

## 4. Frontend Development (08/11/2026–28/11/2026)

Design login page (08/11–11/11)

Build patient request interface (11/11–14/11)

Build food order form and menu (15/11–18/11)

Build maintenance complaint form (19/11–22/11)

Build dashboards and other pages (23/11–28/11)

## 5. Backend Development (16/11/2026–05/12/2026)

Authentication and role permissions (16/11–20/11)

Food order APIs (21/11–26/11)

Maintenance request APIs (27/11–02/12)

Assignment and status updates (03/12–05/12)

## 6. Integration & Testing (06/12/2026–19/12/2026)

Connect frontend and backend (06/12–10/12)

Connect backend and database (11/12–13/12)

Test workflows and permissions (14/12–17/12)

Fix bugs and validate inputs (18/12–19/12)

## 7. Documentation & Delivery (20/12/2026–01/01/2027)

Prepare project documentation (20/12–26/12)

Review and finalize (27/12–29/12)

Prepare presentation (30/12–31/12)

Final system review and submission preparation (01/01/2027)

# 7. Monitoring and Risk Control

Schedule delays: review progress regularly and update the Gantt chart when dates change.

Integration issues: connect and test frontend, backend, and database components step by step.

Requirement changes: record agreed changes in the documentation and task board.

Communication gaps: use the team communication channel and Trello to keep decisions clear.

# 8. Expected Deliverables

Project scope and requirements documentation.

System design diagrams and UI wireframes.

Database schema and tested tables.

Frontend and backend components.

Integrated system with tested food-ordering and maintenance-request workflows.

Final documentation, presentation, and project demonstration prepared before the 2 January 2027 submission.

Note: The GanttProject (.gan) file remains the editable source of the detailed project timeline.